## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-1 | Introduction about Project, System Setup & Text handling | MUST HAVE | NA | Priyusha | 3- Completed
S1 | S1 | US-2 | introduction to project, system setup, multiprocessing , creating a data base | MUST HAVE | NA | Priyusha | 3- Completed
S2 | S2 | US-3 | Actual Implementation with chosing a Text Domain | MUST HAVE | NA | Priyusha | 3- Completed
S2 | S2 | US-3 | Dynamic Chunking, Parallel Processing , multithreading | MUST HAVE | Yield(), re-module, ThreadPoolExecutor, process_chunk() | Priyusha | 3- Completed
S2 | S2 | US-3 | Connecting results to Database | SHOULD HAVE | NA | Priyusha | 3- Completed
S3 | S3 | US-4 | Building of User interface | MUST HAVE | NA | Priyusha | 3- Completed
S3 | S4 | US-5 | Connecting Front end to Backend UI | MUST HAVE | NA | Priyusha | 2- In Progress
S4 | S4 | US-6 | Modifications in UI | SHOULD HAVE | NA | Priyusha | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-1 | T-1 | Introduction of Project | 2026-02-10 | 2026-02-10 | Priyusha | Basics | 3- Completed
US-1 | T-2 | System setup- Install Python & Import libraries | 2026-02-12 | 2026-02-12 | Priyusha | Basics | 3- Completed
US-1 | T-3 | Learning Parallel Processing & Multiprocessing | 2026-02-13 | 2026-02-13 | Priyusha | others | 3- Completed
US-1 | T-4 | Text Handling & Database creation | 2026-02-13 | 2026-02-14 | Priyusha | coding | 3- Completed
US-2 | T-5 | Database collection (Product reviews) | 2006-02-17 | 2006-02-17 | Priyusha | others | 3- Completed
US-3 | T-6 | Dynamic chunking (by_lines & by words) | 2026-02-18 | 2026-02-19 | Priyusha | coding | 3- Completed
US-3 | T-7 | Parallel processing implementation | 2026-02-19 | 2026-02-21 | Priyusha | coding | 3- Completed
US-3 | T-8 | Connecting results to SQLlite | 2026-02-23 | 2026-02-24 | Priyusha | coding | 3- Completed
US-3 | T-9 | Modifications in Backend codes | 2026-02-24 | 2026-02-24 | Priyusha | coding | 3- Completed
US-3 | T-10 | Uploading Files to GitHub Repository | 27/2/2026 | 27/2/2026 | Priyusha | coding | 3- Completed
US-4 | T-11 | Building Basic User Interface | 2026-08-03 | 2026-03-10 | Priyusha | design | 3- Completed
US-4 | T-12 | Adding extra Functionalities | 15/3/2026 | 18/3/2026 | Priyusha | design | 3- Completed
US-5 | T-13 | Modifications in UI | 20/3/26 |  | Priyusha | design | 2- In Progress
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
US-1 |  | Implementng parallel processing | discussed in meeting
US-2 |  | Dynamic chunking | reached out mentor

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7